## WorkA
View Name | Est (min) | Migrated To UDF | Redefined View | Wrapped in SPROC (With Correct Outbound Schema)
Agency_Profile_Update | 10 | X
Alternative_Encounter | 10 | X
ASQ_3 | 10 | X
Client_and_Infant_Health_or_TCM_Medicaid | 10 | X
Client_Funding_Source | 10 | X
Clinical_IPV_Assessment | 10 | X
Community_Advisory_Board_Meeting | 10 | X
Course_Completion | 10 | X
DANCE_Coding_Sheet | 10 | X
Demographics | 10 | X
Demographics_Update | 10 | X
Edinburgh_Postnatal_Depression_Scale | 10 | X
Education_Registration | 10 | X
Education_Registration_V2 | 10 | Duplicate
GAD_7 | 10 | X
Goodwill_Indy_Additional_Referral_Data | 10 | X
Health_Habits | 10 | X
Home_Visit_Encounter | 10 | X
Infant_Birth | 10 | X
Infant_Health_Care | 10 | X
Joint_Visit_Observation | 10 | X
Joint_Visit_Observation_Form | 10 | X
Maternal_Health_Assessment | 10 | X
MN_12_Month_Infant | 10 | X
MN_18_Months_Toddler | 10 | X
MN_24_Month_Toddler | 10 | X
MN_6_Months_Infant | 10 | X
MN_Child_Intake | 10 | X
MN_Primary_Caregiver_Closure | 10 | X
MN_Primary_Caregiver_Intake | 10 | X
New_Hire_Form | 10 | X
New_Hire_V2 | 10 | X
NFP_Los_Angeles__Outreach_Marketing | 10 | X
NFP_Tribal_Project | 10 | X
Nurse_Assessment | 10 | X
PHQ_9 | 10 | X
Profile_Of_Program_Staff_UPDATE | 10
Record_of_Team_Meetings_and_Case_Conferences | 10
Referrals_To_NFP_Program | 10
Relationship_Assessment | 10
Staff_Team_to_Team_Transfer_Request | 10
STAR_Framework | 10
Supplemental_Discharge_Information | 10
TCM_Finance_Log | 10
TCM_ISP | 10
Telehealth_Form | 10
Telehealth_Pilot_Form | 10
TEST_CASE_ASSESSMENT | 10
TX_THV_Supplemental_Data_Form | 10
Unknown | 10
Use_Of_Government_and_Community_Services | 10
WA_MIECHV_Supplemental_HVEF | 10
Weekly_Supervision_Record | 10
530
8.8333

## Est
Task Name | Est | Completed
Work A | 1 DAY
Package Review | 4 Hours